## HOTO Details
|  |  | 100 | 100 | [18 empty] | 58 | [6 empty] | 13144.5 | 14684.6 | 1293.1
S/N. | BL Region | BL Zone | Generic Site ID | Site Code | Collocated Site Code (if any) | Power Status | Site Type | District | Thana | Address | Lat | Long | Security Guard Available | Access Key Status | Outgoing Vendor Name | Incoming Vendor Name | FLM Vendor Office Location | Vendor Transformation | HOTO Plan Date (Primary) | Remarks on HOTO Plan, if any | Outgoing Vendor POC | Incoming Vendor POC | HOTO Actual Date | DG Brand (Including DG-2, if any) | DG Capacity in KVA | DG Fuel Tank Capacity in Ltr. | Fuel Tank Type | DG Present Status on HOTO Date (OK/NOK) | DG Present RH on HOTO Date | DG Present Fuel (Ltr.) with Sediment | DG Present Fuel (Ltr.) including impurity | Additional impurity (water in Ltr.) on top of pure fuel and sediment, if any | GENSET ON Alarm Status (OK/NOK) | Site Type (Standard/Remote) | DG Major Deficiencies After HOTO, if any | Incoming Vendor Comment | HOTO data acknowledged by Outgoing Vendor (Yes/No) | Outgoing Vendor Comment
1 | RO-2 | Sylhet | SYL0133 | SYL_X0133 | SYL_X0133 | CP+DG | Indoor GF | Sylhet | Companiganj Syl. | Tuker Bazar,Companiganj, Sylhet | 25.1084 | 91.7578 |  | Dash Link | DITL | ACL |  | Dhaly-Alliance | 2026-09-12
2 | RO-2 | Sylhet | SYL0082 | SYL_X0082 | SYL_X0082 | CP+DG | Indoor GF | Habiganj | Lakhai | A. Rashid Talukder, West Bulla, Bulla Bazar | 24.3069 | 91.2954 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-05 |  |  |  | 2026-09-07 | Mets | 22 | 2000 |  | OK | 2.9 | 386 | 431 | 45 | OK |  | 1. DG Dynamo faulty - Faulty
3 | RO-2 | Sylhet | SYL0589 | SYL_X0589 | SYL_X0589 | CP+DG | Outdoor GF | Sylhet | Companiganj Syl. | Volagonj Bazar, Companiganj, Sylhet | 25.1385 | 91.7494 |  | Outdoor Cabinet Key | DITL | ACL |  | Dhaly-Alliance | 2026-09-12
4 | RO-2 | Sylhet | SYL0331 | SYL_X0331 | SYL_X0331 | CP+DG | Indoor GF | Habiganj | Habiganj Sadar | Paddarbari Road, Habiganj Sadar, Habiganj | 24.3544 | 91.4223 |  | Old Abloy _510 BL M (3) | DITL | ACL |  | Dhaly-Alliance | 2026-09-03 |  |  |  | 2026-09-07 | FG Wilson | 30 | 1000 |  | OK | 1169 | 195 | 245 | 50 | OK | Standard
5 | RO-2 | Sylhet | SYL0073 | SYL_X0073 | SYL_X0073 | CP+DG | Outdoor GF | Sylhet | Companiganj Syl. | Ichhakolosh, Companygonj, Sylhet | 25.0807 | 91.758 | Yes | Mobuj & Outdoor key | DITL | ACL |  | Dhaly-Alliance | 2026-08-26 |  |  |  | 2026-08-30 | Fg wilson | 22 | 2000 | Can | NOK | 42.2 | 14 | 14 | 00 | OK | Standard | 1.DG Battery faulty. 2.DG Battery cable aluminium need to change. 3.Hose pipe leakage. 4.Hi temperature sensor broken. 5.DG Dynamo faulty. 6.Silencer pipe leakage. 7.DG Room gate broken. 8.DG canopy lock faulty 9.1 Phase missing 10.Fuel thief aria need to proper protection. 11.1 pcs Transformer Faulty. 12.Last servicing date not found.
6 | RO-2 | Sylhet | SYL0117 | SYL_X0117 | SYL_X0117 | CP+DG | Indoor GF | Habiganj | Lakhai | College Road, Bamai, Lakhai, Habiganj,Sylhet | 24.2822 | 91.2532 |  | HMBR | DITL | ACL |  | Dhaly-Alliance | 2026-09-05 |  |  |  | 2026-09-04 | FG Wilson | 22 | 2000 |  | OK | 479 | 250 | 250 |  | OK | Standard
7 | RO-2 | Sylhet | SYL0566 | SYL_X0566 | SYL_X0566 | CP+DG | Indoor GFRT | Habiganj | Lakhai | Bottola Bazar, Lakhai,Habiganj | 24.2892 | 91.216 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-05
8 | RO-2 | Sylhet | SYL0162 | SYL_X0162 | SYL_X0162 | CP+DG | Indoor GF | Sylhet | Companiganj Syl. | Salutikor Bazar, Gowainghat, Sylhet | 24.9962 | 91.8461 | Yes | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-08-26 |  |  |  | 2026-08-30 | Fg wilson | 22 | 2000 | Can | OK | 105.7 | 223 | 223 | 00 | OK | Standard | 1) Dg fan belt not ok 2) Lube oil sensor & Temp sensor disconnected.
9 | RO-2 | Sylhet | SYL0585 | SYL_G0585 | SYL_G0585 | CP+DG | Outdoor GF | Sylhet | Companiganj Syl. | Mayar Bazar, Companiganj, Sylhet | 25.1627 | 91.807 |  | Mobuj & Outdoor key | DITL | ACL |  | Dhaly-Alliance | 2026-09-13
10 | RO-2 | Sylhet | SYL0550 | SYL_X0550 | SYL_X0550 | CP+DG | Indoor GFRT | Moulavibazar | Moulavibazar | Harinagar bazar,Nobiganj,Sylhet | 24.6647 | 91.52 |  | SOLTE | DITL | ACL |  | Dhaly-Alliance | 2026-09-07
11 | RO-2 | Sylhet | SYL0291 | SYL_X0291 | SYL_X0291 | CP+DG | Indoor GF | Habiganj | Bahubal | Dubai Bazar, Bahubal, Habiganj | 24.3866 | 91.5535 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-06 |  |  |  | 2026-09-06 | FG Wilson | 30 | 2000 |  | OK | 3947 | 379 | 394 | 15 | OK |  | 1. DG Room roof tin faulty - Faulty
12 | RO-2 | Sylhet | SYL0087 | SYL_X0087 | SYL_X0087 | CP+DG | Outdoor GF | Sunamganj | Bishwamvarpur | Bishwambarpur, Sunamganj, Sylhet | 25.1027 | 91.3003 | Yes | Mobuj & Outdoor key | DITL | ACL |  | Dhaly-Alliance | 2026-09-07 |  |  |  | 2026-09-04 | Tempest | 20 | 2000 | Can | OK | 446.4 | 212 | 212 |  | OK | Standard
13 | RO-2 | Sylhet | SYL0097 | SYL_X0097 | SYL_X0097 | CP+DG | Indoor RT | Moulavibazar | Moulvibazar Sadar | Md. Syed Mohammed Ali,Village Bekamura,Kazirbazar, Moulovibazar,Sylhet | 24.5726 | 91.7225 |  | Dash Link | DITL | ACL |  | Dhaly-Alliance | 2026-09-05 |  |  |  | 2026-09-07 | FG Wilson | 22 | 65 |  | OK | 64.2 | 63 | 63 |  | OK | Standard | 1. DG room dusty - Faulty 2. DG Room Light (ডিজি রুমের লাইট) - Faulty 3. DG room roof tin faulty - Faulty
14 | RO-2 | Sylhet | SYL0274 | SYL_X0274 | SYL_X0274 | CP+DG | Indoor GF | Sunamganj | Bishwamvarpur | Bagberbazar, Bishwamvarpur, Sunamganj | 25.125 | 91.3689 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-07
15 | RO-2 | Sylhet | SYL0065 | SYL_X0065 | SYL_X0065 | CP+DG | Indoor GF | Sylhet | Kanaighat | Dhaliachar, Kanaighat, Sylhet | 25.0062 | 92.2575 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-14
16 | RO-2 | Sylhet | SYL0219 | SYL_X0219 | SYL_X0219 | CP+DG | Indoor GFRT | Sylhet | Kanaighat | Soroker Bazar, Kanaighat (Zaflon Road), Sylhet | 24.992 | 92.3426 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-15
17 | RO-2 | Sylhet | SYL0257 | SYL_X0257 | SYL_X0257 | CP+DG | Indoor GF | Moulavibazar | Moulvibazar Sadar | Thana Bazar, Moulvibazar Sadar,Moulvibazar | 24.5225 | 91.7276 | No | New Abloy _DMO (1) | DITL | ACL |  | Dhaly-Alliance | 2026-09-09 |  |  |  | 2026-09-03 | FG Wilson | 22 | 2000 | Can | OK | 633 | 223 | 223 |  | OK | Standard | 1. Hi temp sensor - Faulty 2. DG Rusty - Faulty
18 | RO-2 | Sylhet | SYL0233 | SYL_X0233 | SYL_X0233 | CP+DG | Indoor GF | Sylhet | Kanaighat | Chatul Bazar, Kanaighat, Sylhet | 25.0529 | 92.1748 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-14
19 | RO-2 | Sylhet | SYL0092 | SYL_X0092 | SYL_X0092 | CP+DG | Outdoor GF | Moulavibazar | Moulavibazar | Moshahid AW, Inatganj, Nabiganj, Habiganj | 24.6651 | 91.5622 | Yes | SAFAR & Outdoor key | DITL | ACL |  | Dhaly-Alliance | 2026-09-06 |  |  |  | 2026-09-07 | FG Wilson | 30 | 2000 |  | OK | 90.3 | 315 | 315 |  | OK |  | 1. Fuel Pipe (ফুয়েল পাইপ) - Faulty 2. DG CB Problematic - Faulty
20 | RO-2 | Sylhet | SYL0613 | SYL_X0613 | SYL_X0613 | CP+DG | Outdoor GF | Sunamganj | Bishwamvarpur | Bhaddertek, P.O: Rotagaw-3000, Bishwamvarpur, Sunamganj | 25.0927 | 91.3779 | Yes | Outdoor Cabinet Key | DITL | ACL |  | Dhaly-Alliance | 2026-08-27 |  |  |  | 2026-08-31 | FG Wilson | 22 | 2000 | Can | OK | 4345.3 | 134 | 149 | 15 | OK | Standard | Lube oil shootees
21 | RO-2 | Sylhet | SYL0235 | SYL_X0235 | SYL_X0235 | CP+DG | Indoor GFRT | Sylhet | Zakiganj | Atgram Bazar, Zakiganj, Sylhet | 24.9864 | 92.3999 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-15
22 | RO-2 | Sylhet | SYL0218 | SYL_X0218 | SYL_X0218 | CP+DG | Indoor GF | Sylhet | Kanaighat | Rajagonj Bazar, Kanaighat, Sylhet | 24.9034 | 92.0654 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-16
23 | RO-2 | Sylhet | SYL0020 | SYL_X0020 | SYL_X0020 | CP+DG | Indoor GF | Sylhet | Zakiganj | near Sagbag Market on the Sylhet-Jakiganj highway | 24.97 | 92.2646 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-15
24 | RO-2 | Sylhet | SYL0273 | SYL_X0273 | SYL_X0273 | CP+DG | Indoor GFRT | Sylhet | Kanaighat | Suraighat Bazar,Kanaighat, Sylhet | 25.0623 | 92.2588 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-16
25 | RO-2 | Sylhet | SYL0204 | SYL_X0204 | SYL_X0204 | CP+DG | Indoor GFRT | Sylhet | Gowainghat | Hadarpar Bazar, Gowainghat, Sylhet | 25.1475 | 91.8881 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-13
26 | RO-2 | Sylhet | SYL0200 | SYL_X0200 | SYL_X0200 | CP+DG | Indoor GFRT | Sylhet | Beanibazar | Dubag Bazar, Beanibazar, Sylhet | 24.8819 | 92.2099 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-17
27 | RO-2 | Sylhet | SYL0069 | SYL_X0069 | SYL_X0069 | CP+DG | Indoor GFRT | Sunamganj | Jamalganj | Upozilla Quarter, Jamalganj, Sunamganj, Sylhet | 25.0004 | 91.2328 | Yes | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-08-28 |  |  |  | 2026-09-01 | SDMO | 30 | 2000 | Can | NOK | 2952.9 | 55 | 114 | 59 | NOK | Remote | DG permanent faulty | DG permanent faulty
28 | RO-2 | Sylhet | SYL0222 | SYL_X0222 | SYL_X0222 | CP+DG | Indoor GF | Habiganj | Chunarughat | Sakir Md. Bazar, Chunarughat, Habiganj , Sylhet | 24.2231 | 91.4706 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-06 |  |  |  | 2026-09-05 | Tempest | 22 | 2000 |  | NOK | 2958 | 345 | 345 | 00 |  | Standard
29 | RO-2 | Sylhet | SYL0142 | SYL_X0142 | SYL_X0142 | CP+DG | Indoor GF | Sylhet | Beanibazar | Boiragibazar, Beanibazar, Sylhet | 24.853 | 92.1575 |  | Local | DITL | ACL |  | Dhaly-Alliance | 2026-09-17
30 | RO-2 | Sylhet | SYL0118 | SYL_X0118 | SYL_X0118 | CP+DG | Indoor GF | Sylhet | Beanibazar | Abdullahpur, P.O- Paton, P.S. -Beanibazar, Sylhet | 24.7735 | 92.1678 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-19
31 | RO-2 | Sylhet | SYL0604 | SYL_X0604 | SYL_X0604 | CP+DG | Indoor GF | Habiganj | Habiganj Sadar | Alipur, PO: Shah Haji Bazar, Union: Nurpur, Habiganj Sadar, Habiganj |  |  |  | Local | DITL | ACL |  | Dhaly-Alliance | 2026-09-07 |  |  |  | 2026-09-06 | FG Wilson | 30 | 2000 |  | OK | 3421 | 163 | 163 |  | OK | Standard
32 | RO-2 | Sylhet | SYL0483 | SYL_X0483 | SYL_X0483 | CP+DG | Indoor GF | Sylhet | Beanibazar | Dewnagar, Sheola Bazar, Beanibazar, Sylhet | 24.8913 | 92.1895 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-17
33 | RO-2 | Sylhet | SYL0052 | SYL_X0052 | SYL_X0052 | CP+DG | Indoor GF | Habiganj | Nabiganj | Vill: Sataihal, Thana Nabiganj, Dist: Habiganj, SDH Tower Sharing Sylhet. | 24.4831 | 91.5781 |  | Local | DITL | ACL |  | Dhaly-Alliance | 2026-09-06
34 | RO-2 | Sylhet | SYL0089 | SYL_X0089 | SYL_X0089 | CP+DG | Outdoor GF | Sunamganj | Jamalganj | Gozaria Bazar, Jamalganj, Sunamganj, Sylhet | 24.8791 | 91.1638 | Yes | Local & Outdoor key | DITL | ACL |  | Dhaly-Alliance | 2026-08-28 |  |  |  | 2026-09-01 | Tempest | 20 | 2000 | Can | OK | 2241 | 104 | 104 |  | OK | Remote | 1. Over Run - Faulty | Need to servicing
35 | RO-2 | Sylhet | SYL0420 | SYL_G0420 | SYL_G0420 | CP+DG | Indoor GFRT | Sunamganj | Jamalganj | Laxmipur bazar, Jamalganj, Sunamganj | 24.9166 | 91.2289 | Yes | Local | DITL | ACL |  | Dhaly-Alliance | 2026-08-28 |  |  |  | 2026-09-01 | Tempest | 22 | 2000 | Can | OK | 3498.4 | 178 | 297 | 119 | OK | Remote | 1. Radiator fully block dust - Faulty | 1) Hedgasket problem 2) Rediotor jum/ not cilin
36 | RO-2 | Sylhet | SYL0364 | SYL_X0364 | SYL_X0364 | CP+DG | Indoor GF | Moulavibazar | Moulvibazar Sadar | Moulvibazar Sadar,Moulvibazar , sylhet | 24.4455 | 91.6759 | Yes | Local | DITL | ACL |  | Dhaly-Alliance | 2026-09-12 |  |  |  | 2026-09-03 | FG Wilson | 30 | 2000 | Can | OK | 146.4 | 394 | 394 | 00 | OK | Standard
37 | RO-2 | Sylhet | SYL0062 | SYL_X0062 | SYL_X0062 | CP+DG | Outdoor GF | Sylhet | Sylhet Sadar | Shiber Bazar, Sylhet sadar, Sylhet | 24.9762 | 91.7884 |  | Mobuj & Outdoor key | DITL | ACL |  | Dhaly-Alliance | 2026-09-12
38 | RO-2 | Sylhet | SYL0017 | SYL_X0017 | SYL_X0017 | CP+DG | Indoor GF | Sylhet | Jaintiapur | Khorkapunji near Dorbosto Bazar on Sylhet Jaintapur highway | 25.0475 | 92.0962 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-14
39 | RO-2 | Sylhet | SYL0075 | SYL_X0075 | SYL_X0075 | CP+DG | Outdoor GF | Moulavibazar | Juri | Katchbazar,Kaminiganj nowabazae | 24.5909 | 92.1146 | Yes | Local & Outdoor key | DITL | ACL |  | Dhaly-Alliance | 2026-09-06 |  |  |  | 2026-09-02 | Tempest | 22 | 2000 | Can | OK | 4181 | 230 | 230 | 00 | OK | Standard | DG room light faulty
40 | RO-2 | Sylhet | SYL0191 | SYL_X0191 | SYL_X0191 | CP+DG | Indoor GF | Sunamganj | Sunamganj Sadar | Mongolkata bazar, Sunamganj, Sylhet | 25.1305 | 91.4266 | No | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-08 |  |  |  | 2026-09-05 | FG Wilson | 22 | 2000 | Can | OK | 15796.7 | 241 | 241 |  | OK | Remote | 1. Lube oil level is low - Faulty 2. MC 1 pole faulty - Faulty 3. Need Overhaling - Faulty
41 | RO-2 | Sylhet | SYL0002 | SYL_X0002 | SYL_X0002 | CP+DG | Indoor RT | Sylhet | Sylhet Sadar | Sylhet Mellenium Shopping Complex, Jallarpar road, Zindabazar, Sylhet | 24.8947 | 91.8667 |  | N/A | DITL | ACL |  | Dhaly-Alliance | 2026-09-10
42 | RO-2 | Sylhet | SYL0043 | SYL_X0043 | SYL_X0043 | CP+DG | Indoor GF | Sunamganj | South Sunamgonj | Villege: Joykolas,Thana: Sunamganj, District: Sunamganj, Division: Sylhet | 24.9509 | 91.3982 | No | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-08-29 |  |  |  | 2026-08-31 | Fg wilson | 22 | 2000 | Can | OK | 442.8 | 149 | 186 | 37 | OK | Standard | 1. DG Fan Belt Loose - Faulty Note: 1) Dg fan belt loss 2)charging dynamo properly not setting 3) engine lube oil shortest | 1) Dg fan belt loss, 2)Charging dynamo properly not setting 3) engine lube oil shortest
43 | RO-2 | Sylhet | SYL0568 | SYL_X0568 | SYL_X0568 | CP+DG | Outdoor GFRT | Sunamganj | Sunamganj Sadar | Tuker Bazar, Sunamganj Sadar, Sunamganj | 25.0305 | 91.3586 | No | Mobuj & Outdoor key | DITL | ACL |  | Dhaly-Alliance | 2026-08-29 |  |  |  | 2026-08-31 | Welland Power | 20 | 2000 | Can | OK | 2950.21 | 282 | 297 | 15 | OK | Standard
44 | RO-2 | Sylhet | SYL0077 | SYL_X0077 | SYL_X0077 | CP+DG | Indoor GF | Moulavibazar | Rajnagar | Mr. Batir Miah, Dhakkhin gaw, Munshibazar, Rajnagar, Moulvibazar, Sylhet | 24.5821 | 91.8908 | Yes | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-08-29 |  |  |  | 2026-09-01 | Visa | 30 | 2000 | Can | OK | 629.2 |  | 327 |  | OK |  | DG Fuel pipe hard need to change Need to DG Radiator servicing DG Room light faulty Need to Fuel tank locking system
45 | RO-2 | Sylhet | SYL0242 | SYL_X0242 | SYL_X0242 | CP+DG | Indoor GFRT | Sunamganj | Sunamganj Sadar | Betganj Bazar, Sunamganj Sadar, Sunamganj | 25.0246 | 91.4427 | Yes | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-08 |  |  |  | 2026-09-02 | FG Wilson | 22 | 2000 | Can | OK | 2635.2 | 104 | 104 |  | OK | Standard | 1. Lube Oil Shortage - Faulty
46 | RO-2 | Sylhet | SYL0213 | SYL_X0213 | SYL_X0213 | CP+DG | Indoor GFRT | Moulavibazar | Barlekha | Office Bazar, Barlekha, Moulvibazar | 24.765 | 92.2246 | Yes | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-05 |  |  |  | 2026-09-03 | FG Wilson | 22 | 2000 | Can | OK | 9627 | 290 | 312 | 22 | OK | Standard | 1. ATS hole filling nok - Not Available 2. DG Room Light (ডিজি রুমের লাইট) - Faulty
47 | RO-2 | Sylhet | SYL0141 | SYL_X0141 | SYL_X0141 | CP+DG | Outdoor GF | Moulavibazar | Barlekha | Shaypur, Shahbazpur, Barlekha, Moulvibazar | 24.8045 | 92.2412 | Yes | Outdoor Cabinet Key | DITL | ACL |  | Dhaly-Alliance | 2026-09-03 |  |  |  | 2026-09-02 | Himonshi | 30 | 2000 | Can | OK | 1734 | 245 | 225 | 20 | OK | Standard | 1. DG overholing issue - Faulty
48 | RO-2 | Sylhet | SYL0615 | SYL_X0615 | SYL_X0615 | CP+DG | Outdoor GF | Moulavibazar | Kulaura | Kathaltoli Bazar, Kormoda, Kulaura, Moulvibazar | 24.4397 | 92.0219 | Yes | Outdoor Cabinet Key | DITL | ACL |  | Dhaly-Alliance | 2026-09-07 |  |  |  | 2026-09-02 | Mets | 22 | 2000 | Can | OK | 312 | 282 | 297 | 12 | OK | Standard | 1. Fuel Pipe (ফুয়েল পাইপ) - Faulty 2. Need to fuel pipe protection for fuel save - Faulty
49 | RO-2 | Sylhet | SYL0611 | SYL_X0611 | SYL_X0611 | CP+DG | Outdoor GF | Sunamganj | Dowarabazar | Vill- Mohabbat Pur, UP- 9 no Surma Union , P/S- Dowarabazar, Dist- Sunamganj | 25.0939 | 91.558 | Yes | Outdoor Cabinet Key | DITL | ACL |  | Dhaly-Alliance | 2026-09-10 |  |  |  | 2026-09-02 | FG Wilson | 30 | 850 | Can | OK | 303.2 | 66 | 122 | 56 | OK | Remote
50 | RO-2 | Sylhet | SYL0405 | SYL_X0405 | SYL_X0405 | CP+DG | Indoor GF | Sylhet | Kanaighat | Bordesh Bazar/ Bagar bazar, Kanaighat, Sylhet | 24.9628 | 92.2116 |  | Duolux | DITL | ACL |  | Dhaly-Alliance | 2026-09-16
51 | RO-2 | Sylhet | SYL0247 | SYL_X0247 | SYL_X0247 | CP+DG | Indoor GFRT | Sunamganj | Dowarabazar | Ambari Bazar, Dowarabazar, Sunamganj | 25.0697 | 91.4758 | No | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-09 |  |  |  | 2026-09-02 | Green Power | 22 | 2000 | Can | OK | 2350.4 | 352 | 352 |  | OK | Standard | 1. DG canopy broken - Faulty 2. DG controller install proper way - Faulty
52 | RO-2 | Sylhet | SYL0086 | SYL_X0086 | SYL_X0086 | CP+DG | Outdoor GF | Sunamganj | Dowarabazar | Dawara Bazar, Sunamganj, Sylhet | 25.0486 | 91.5581 | Yes | Local & Outdoor key | DITL | ACL |  | Dhaly-Alliance | 2026-09-10 |  |  |  | 2026-09-02 | FG Wilson | 22 | 850 | Can | OK | 341.5 | 163 | 179 | 16 | OK | Standard | 1. DG fan bet losse - Faulty 2. Radiator s blocked with dust. - Faulty
53 | RO-2 | Sylhet | SYL0067 | SYL_X0067 | SYL_X0067 | CP+DG | Indoor GF | Moulavibazar | Kulaura | Vill: Alalpur,Thana: Kulaura, District: Moulvibazar, Division: Sylhet | 24.5148 | 92.0341 | Yes | Mobus | DITL | ACL |  | Dhaly-Alliance | 2026-08-30 |  |  |  | 2026-08-31 | FG Wilson | 30 | 2000 | Can | OK |  | 372 | 372 |  | OK | Standard | Lub oil shortage ATS Door cobja broken DG Front side canopy missing DG Base not fixed AC power cable twist DG room light not found
54 | RO-2 | Sylhet | SYL0103 | SYL_X0103 | SYL_X0103 | CP+DG | Indoor GFRT | Moulavibazar | Kulaura | Vill & P.O.- Pretimpasha, Robir Bazar,P. S.- Kulaura, Dist: Moulvibazar | 24.4458 | 91.9928 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-08-30 |  |  |  | 2026-09-02 | Ghadder | 20 | 2000 | Can | OK | 7873 | 354 | 354 |  | OK | Standard | 1. Fuel pipe hard - Faulty 2. Need to fuel tank lock system,& pipe protection - Faulty
55 | RO-2 | Sylhet | SYL0105 | SYL_X0105 | SYL_X0105 | CP+DG | Indoor GF | Moulavibazar | Kamalganj | Munshibazar, Shamshernagar road, PS: Kamalganj, Dist:Maulvibazar | 24.4178 | 91.8454 | Yes | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-03 |  |  |  | 2026-09-03 | Pramac | 22 | 1000 | Can | OK | 277 | 248 | 248 |  | OK | Standard | 1. (unspecified) - Faulty Note: DG canopy open due to hi temp issue, need to DG health check 2. (unspecified) - Faulty Note: ABC Faulty 3. (unspecified) - Faulty Note: DG Room roof tin faulty
56 | RO-2 | Sylhet | SYL0093 | SYL_X0093 | SYL_X0093 | CP+DG | Outdoor RT | Sylhet | Gowainghat | Hotel Peris, Mamar Bazar, Jaflong, Jaintapur, Sylhet | 25.1709 | 92.0175 |  | Outdoor Cabinet Key | DITL | ACL |  | Dhaly-Alliance | 2026-09-13
57 | RO-2 | Sylhet | SYL0537 | SYL_X0537 | SYL_X0537 | CP+DG | Indoor GFRT | Sylhet | Balaganj | Begampur Bazar, Balaganj, Sylhet | 24.6585 | 91.708 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-10
58 | RO-2 | Sylhet | SYL0543 | SYL_X0543 | SYL_X0543 | CP+DG | Outdoor GF | Sunamganj | Dowarabazar | Dowarabazar,Sunamganj,Sylhet | 25.1386 | 91.5759 | Yes | Local | DITL | ACL |  | Dhaly-Alliance | 2026-09-09 |  |  |  | 2026-09-02 | Tempest | 20 | 2000 | Can | OK | 11629.41 | 171 | 297 | 171 | OK | Remote | 1. Dg Controller display not visible - Faulty
59 | RO-2 | Sylhet | SYL0426 | SYL_X0426 | SYL_X0426 | CP+DG | Indoor GF | Sylhet | Fenchuganj | Manik Kona Bazar, Fenchuganj,Sylhet | 24.718 | 91.9858 |  | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-19
60 | RO-2 | Sylhet | SYL0083 | SYL_X0083 | SYL_X0083 | CP+DG | Indoor RT | Habiganj | Ajmiriganj | Azmiriganj Bazar, PS: Azmiriganj, Hobiganj | 24.5588 | 91.232 | Yes | Kiko | DITL | ACL |  | Dhaly-Alliance | 2026-09-03 |  |  |  | 2026-09-07 | FG Wilson | 22 | 2000 |  | OK |  | 386 | 431 | 45 |  | Standard
61 | RO-2 | Sylhet | SYL0397 | SYL_G0397 | SYL_G0397 | CP+DG | Outdoor GF | Sunamganj | Tahirpur | Ekota bazar, halholia,Tahirpur, Sunamganj | 25.1728 | 91.1965 | Yes | Outdoor key | DITL | ACL |  | Dhaly-Alliance | 2026-09-08 |  |  |  | 2026-09-04 | Mets | 22 | 2000 | Can | NOK | 1119 | 124 | 124 |  | OK | Remote | 1. DG lube oil empty - Faulty 2. servicing date run hour over - Faulty 3. Font site canopy missing - Faulty 4. DG back site canopy missing - Faulty Note: Charging dynamo faulty 5. Need to overhaling - Faulty
62 | RO-2 | Sylhet | SYL0072 | SYL_X0072 | SYL_X0072 | CP+DG | Outdoor GF | Habiganj | Baniachong | Thana:Baniachong, District: Habiganj, Division: Sylhet | 24.5183 | 91.3614 |  | Mobuj & Outdoor key | DITL | ACL |  | Dhaly-Alliance | 2026-09-03 |  |  |  | 2026-09-04 | Welland Power | 22 | 2000 |  | OK | 1091 | 295 | 295 |  | OK | Standard
63 | RO-2 | Sylhet | SYL0422 | SYL_G0422 | SYL_G0422 | CP+DG | Outdoor GF | Sunamganj | Tahirpur | Lamagaon, Taherpur, Sunamgonj | 25.1126 | 91.0641 | Yes | Premimum & Outdoor key | DITL | ACL |  | Dhaly-Alliance | 2026-09-10 |  |  |  | 2026-09-06 | FG Wilson | 22 | 2000 | Can | OK | 142 | 277 | 369 | 90 | OK | Remote | 1. No servicing date found. - Faulty
64 | RO-2 | Sylhet | SYL0156 | SYL_X0156 | SYL_X0156 | CP+DG | Indoor GF | Sunamganj | Chhatak | Kumna, Sylhet-Paper Mill, Chhatak, Sunamganj, Sylhet | 25.0222 | 91.6479 | Yes | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-10 |  |  |  | 2026-09-02 | Tempest | 20 | 800 | Can | OK | 2869.14 | 245 | 245 |  | OK | Standard | 1. Dg controller display not clean, Nothing on the display is visible - Faulty 2. Radiator ful block dust - Faulty 3. DG fan belt loose. - Faulty
65 | RO-2 | Sylhet | SYL0152 | SYL_X0152 | SYL_X0152 | CP+DG | Indoor GF | Sunamganj | Tahirpur | Vill+PO: Badaghat bazar,PS:Tahirpur,Sunamganj,Sylhet | 25.1444 | 91.2248 | Yes | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-08 |  |  |  | 2026-09-04 | Tempest | 13 | 2000 | Can | OK | 343.4 | 197 | 197 |  | OK | Remote | 1. DG power breaker faulty - Faulty 2. Engine mountain broken - Faulty
66 | RO-2 | Sylhet | SYL0221 | SYL_X0221 | SYL_X0221 | CP+DG | Indoor GF | Sunamganj | South Sunamgonj | Kandigaon, South Sunamganj, Sunamganj Sadar | 24.9268 | 91.4474 | Yes | Local | DITL | ACL |  | Dhaly-Alliance | 2026-09-09 |  |  |  | 2026-09-05 | FG Wilson | 30 | 2000 | Can | OK | 5653 | 189 | 256 | 67 | OK | Standard | 1. water pump leakage - Faulty
67 | RO-2 | Sylhet | SYL0554 | SYL_X0554 | SYL_X0554 | CP+DG | Indoor GF | Sunamganj | Derai | Vill: Notun Kornogoan, P.O: Derai, P.S: Derai, Dist: Sunamganj | 24.8281 | 91.3603 | No | Mobaj | DITL | ACL |  | Dhaly-Alliance | 2026-09-09 |  |  |  | 2026-09-03 | Pramac | 22 | 1000 | Can | OK | 2472 | 110 | 144 | 34 |  | Standard | 1. Lube oil level is low - Faulty 2. Need to overhaling issue because lube oil is leaking from the engine gasket. - Faulty 3. (unspecified) - Faulty Note: The fuel tank is installed in an open area, fuel could be stolen at any time. 4. Black smoke is coming out of the silencer pipe. - Faulty Note: With the engine turned off 5. when engine start - Faulty
68 | RO-2 | Sylhet | SYL0091 | SYL_X0091 | SYL_X0091 | CP+DG | Indoor GF | Sunamganj | Sullah | Sullah College, Sullah, Sunamganj | 24.6737 | 91.2707 | Yes | Local | DITL | ACL |  | Dhaly-Alliance | 2026-09-09 |  |  |  | 2026-09-03 | Tempest | 20 | 2000 | Can | OK | 4980.27 | 118 | 157 | 39 | OK | Remote | 1. DG controller display not visible - Faulty 2. The radiator is full of dust - Faulty 3. Lube oil level is low - Faulty 4. (unspecified) - Faulty Note: The tin sheets on the site's roof are damaged, and the brickwork on one side has collapsed; the wall needs to be repaired.
69 | RO-2 | Sylhet | DHK0210 | DHK_X0210 |  | CP+DG | Indoor GF | Narsingdi | Raipura | Lochanpur,North Bakhornagar,Raypura ,Narsingdi | 24.0309 | 90.868 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-05 | Expected DG Capacity: 30 KVA
70 | RO-2 | Sylhet | DHK0213 | DHK_X0213 |  | CP+DG | Indoor GF | Narsingdi | Narsingdi Sadar | Vill;Sonar, Mouza;Kaksia, Narsingdi sadar, Narsingdi., Will share SDH Tower | 23.8922 | 90.6501 |  |  | DITL | ACL |  | Dhaly-Alliance |  | Expected DG Capacity: 30 KVA |  |  | 2026-08-17 | Tempest | 30 | 2000 |  | OK | 85506 | 179 | 253 | 74 | OK | Standard |  | Digitized from scanned paper HOTO checklist (Narsingdi zone backfill).
71 | RO-2 | Sylhet | DHK0231 | DHK_X0231 |  | CP+DG | Outdoor GF | Kishoreganj | Bhairab | Mizan Group Steel Mills, Kamalpur, Bhairab, Kishoreganj | 24.0621 | 90.9782 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-03 | Expected DG Capacity: 22 KVA
72 | RO-2 | Sylhet | DHK0750 | DHK_X0750 |  | CP+DG | Indoor GF | Narsingdi | Palash | Charpara, Ghorashal, Palash, Narshingdi | 23.9429 | 90.6222 |  |  | DITL | ACL |  | Dhaly-Alliance |  | Expected DG Capacity: 22 KVA |  |  | 2026-09-02 | Tempest | 20 | 2000 |  | OK |  | 296.1 | 328 | 31.9 | OK | Standard | 1. DG Room Light - Faulty Note: Faulty 2. Canopy - Faulty Note: One part canopy open 3. Controller Sensor - Faulty Note: DG Controller box open | Digitized from scanned paper HOTO checklist (Narsingdi zone backfill).
73 | RO-2 | Sylhet | DHK1097 | DHK_X1097 |  | CP+DG | Indoor GF | Narsingdi | Narsingdi Sadar | Nazim Uddin, Shaheb protap more, P.O. : Baghata, Narsingdi | 23.9092 | 90.6879 |  |  | DITL | ACL |  | Dhaly-Alliance |  | Expected DG Capacity: 30 KVA |  |  | 2026-09-01 | FG Wilson | 30 | 2000 |  | OK | 7371 | 183 | 183 |  | OK | Standard |  | Digitized from scanned paper HOTO checklist (Narsingdi zone backfill). NOTE: handover date not legible on original form -- estimated from batch pattern, needs Narsingdi team confirmation.
74 | RO-2 | Sylhet | DHK1171 | DHK_X1171 |  | CP+DG | Indoor GF | Narsingdi | Raipura | Vill:- Hasempur,Post & Thana:-Raipura,Narsingdi. | 23.9847 | 90.8758 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-05 | Expected DG Capacity: 22 KVA
75 | RO-2 | Sylhet | DHK1648 | DHK_X1648 |  | CP+DG | Indoor GF | Narsingdi | Shibpur | Md. Momen Miah & Others,Md. Momen Miah & Others, Vill- Gonergaon, P.S. Madhobpur, Shibpur, Narsingdi.01711-001302 | 23.9623 | 90.7382 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-05 | Expected DG Capacity: 22 KVA
76 | RO-2 | Sylhet | DHK1669 | DHK_X1669 |  | CP+DG | Indoor GF | Kishoreganj | Kuliarchar | Chhaysuti(Near Chhaysuti Bazar), Kuliarchar, Kishorganj. | 24.1254 | 90.914 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-05 | Expected DG Capacity: 13 KVA
77 | RO-2 | Sylhet | DHK1674 | DHK_X1674 |  | CP+DG | Indoor GF | Narsingdi | Shibpur | Itakhola Circle, Shibpur, Narshingdi, Dhaka | 23.9795 | 90.7345 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-06 | Expected DG Capacity: 22 KVA
78 | RO-2 | Sylhet | DHK1801 | DHK_X1801 |  | CP+DG | Indoor GF | Narsingdi | Narsingdi Sadar | modhupur,algi ,Madhobdi, Norsinghdi, Narsingdi Sadar, Narsingdi. | 23.8416 | 90.6687 |  |  | DITL | ACL |  | Dhaly-Alliance |  | Expected DG Capacity: 22 KVA |  |  | 2026-09-01 | Welland Power | 22 |  |  | OK | 1289.2 | 253 | 253 |  | OK | Standard | 1. Controller Sensor - Faulty Note: DG Controller condition very poor | Digitized from scanned paper HOTO checklist (Narsingdi zone backfill). NOTE: handover date not legible on original form -- estimated from batch pattern, needs Narsingdi team confirmation.
79 | RO-2 | Sylhet | DHK1805 | DHK_X1805 |  | CP+DG | Indoor GF | Narsingdi | Narsingdi Sadar | Pakuria, Narshingdi sadar, Dhaka | 23.8924 | 90.6248 |  |  | DITL | ACL |  | Dhaly-Alliance |  | Expected DG Capacity: 22 KVA |  |  | 2026-09-01 | Tempest | 22 |  |  | OK | 308.6 | 338 | 380 | 42 | OK | Standard | 1. Controller Sensor - Faulty Note: DG Controller Box faulty | Digitized from scanned paper HOTO checklist (Narsingdi zone backfill). NOTE: handover date not legible on original form -- estimated from batch pattern, needs Narsingdi team confirmation.
80 | RO-2 | Sylhet | DHK1806 | DHK_X1806 |  | CP+DG | Indoor GF | Kishoreganj | Bhairab | Kalikaprasad, Uttarpar, Bhairab, Kishoreganj, Dhaka | 24.091 | 90.9379 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-02 | Expected DG Capacity: 22 KVA
81 | RO-2 | Sylhet | DHK1879 | DHK_X1879 |  | CP+DG | Indoor GF | Narsingdi | Shibpur | Md.Jakir Hassan,Garbari bazar,Shibpur,Narsingdi | 24.0686 | 90.6927 |  |  | DITL | ACL |  | Dhaly-Alliance |  | Expected DG Capacity: 22 KVA |  |  | 2026-09-01 | Gentec | 20 | 1000 |  | OK | 540.6 | 206.2 | 236 | 29.8 | OK | Standard | 1. BTS Room Condition - Faulty Note: DG Room condition very poor 2. Radiator - Faulty Note: DG condition poor - need radiator mounting | Digitized from scanned paper HOTO checklist (Narsingdi zone backfill).
82 | RO-2 | Sylhet | DHK1914 | DHK_X1914 |  | CP+DG | Indoor GF | Narsingdi | Manohardi | Md. Aminul Haque Master, Chalakchar, Monohardi, Narsingdi | 24.1907 | 90.7295 |  |  | DITL | ACL |  | Dhaly-Alliance |  | Expected DG Capacity: 22 KVA |  |  | 2026-09-01 | Stamford | 20 | 2000 |  | OK | 9424.46 | 263 | 285 | 22 | OK | Standard | 1. BTS Room Condition - Faulty Note: DG Room condition very poor 2. DG Room Light - Faulty Note: Faulty 3. Fuel Tank Lock System - Faulty Note: Faulty | Digitized from scanned paper HOTO checklist (Narsingdi zone backfill).
83 | RO-2 | Sylhet | DHK1925 | DHK_X1925 |  | CP+DG | Indoor GF | Narsingdi | Shibpur | C & B Bazar, Shibpur, Narsingdi, Dhaka | 24.0802 | 90.733 |  |  | DITL | ACL |  | Dhaly-Alliance |  | Expected DG Capacity: 22 KVA |  |  | 2026-09-01 | Welland Power | 22 | 2000 |  | OK | 1235.7 | 261 | 305 | 44 | OK | Standard |  | Digitized from scanned paper HOTO checklist (Narsingdi zone backfill).
84 | RO-2 | Sylhet | DHK2063 | DHK_X2063 |  | CP+DG | Indoor GF | Narsingdi | Shibpur | Kundar Para, Shibpur, Narsingdi, Dhaka | 23.9989 | 90.7677 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-07 | Expected DG Capacity: 30 KVA
85 | RO-2 | Sylhet | DHK2119 | DHK_X2119 |  | CP+DG | Indoor GF | Narsingdi | Raipura | Mizan, radhaganj Bazar, Raipura, Narsingdi | 23.9773 | 90.8111 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-06 | Expected DG Capacity: 22 KVA
86 | RO-2 | Sylhet | DHK2551 | DHK_X2551 |  | CP+DG | Indoor GF | Narsingdi | Belabo | Dulal Kandi Bazar, Belabo, Narsingdi, Dhaka | 24.0808 | 90.8815 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-03 | Expected DG Capacity: 22 KVA
87 | RO-2 | Sylhet | DHK2655 | DHK_X2655 |  | CP+DG | Indoor GFRT | Kishoreganj | Bhairab | Madhher char, Choudhury bazar, Bhairab, Kishoreganj. | 24.0921 | 90.9752 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-03 | Expected DG Capacity: 22 KVA
88 | RO-2 | Sylhet | DHK2656 | DHK_X2656 |  | CP+DG | Indoor GFRT | Kishoreganj | Kuliarchar | Barkarchar , Kuliar Char , Kuliar Char, Kishoreganj. | 24.1623 | 90.9307 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-03 | Expected DG Capacity: 22 KVA
89 | RO-2 | Sylhet | DHK2681 | DHK_X2681 |  | CP+DG | Indoor GF | Narsingdi | Narsingdi Sadar | Narsingdi sadar, Narsingdi | 23.9257 | 90.708 |  |  | DITL | ACL |  | Dhaly-Alliance |  | Expected DG Capacity: 30 KVA |  |  | 2026-08-31 | FG Wilson | 30 | 2000 |  | OK | 3389 | 419 | 419 |  | OK | Standard |  | Digitized from scanned paper HOTO checklist (Narsingdi zone backfill).
90 | RO-2 | Sylhet | DHK2727 | DHK_X2727 |  | CP+DG | Indoor GFRT | Narayanganj | Araihazar | Jangalia bazar,Arihazar,Narayangonj | 23.7347 | 90.6763 |  |  | DITL | ACL |  | Dhaly-Alliance |  | Expected DG Capacity: 22 KVA |  |  | 2026-09-02 | Tempest | 20 | 2000 |  | OK | 220.5 | 293 | 327 | 34 | OK | Standard | 1. Radiator - Faulty Note: DG Radiator mounting broken 2. Genset Alarm - Faulty Note: DG Run Alarm probably needs wiring 3. DG Room Light - Faulty Note: DG Room wiring faulty | Digitized from scanned paper HOTO checklist (Narsingdi zone backfill).
91 | RO-2 | Sylhet | DHK2941 | DHK_X2941 |  | CP+DG | Indoor GFRT | Narsingdi | Belabo | Narayanpur Bazar, Belabo, Narsingdi. | 24.0587 | 90.9208 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-06 | Expected DG Capacity: 22 KVA
92 | RO-2 | Sylhet | DHK3450 | DHK_X3450 |  | CP+DG | Indoor GFRT | Kishoreganj | Bhairab | Milon,Dori Chondiber Mor,Bhairab,Kishoreganj | 24.0761 | 90.9834 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-02 | Expected DG Capacity: 22 KVA
93 | RO-2 | Sylhet | DHK3451 | DHK_X3451 |  | CP+DG | Indoor GFRT | Narsingdi | Shibpur | Bannar Bazar, Shibpur, Narsingdi | 24.0084 | 90.705 |  |  | DITL | ACL |  | Dhaly-Alliance |  | Expected DG Capacity: 22 KVA |  |  | 2026-09-01 | Tempest | 20 | 2000 |  | OK | 3898.27 | 285.6 | 290 | 4.4 | OK | Standard |  | Digitized from scanned paper HOTO checklist (Narsingdi zone backfill).
94 | RO-2 | Sylhet | DHK3470 | DHK_X3470 |  | CP+DG | Indoor GF | Narsingdi | Raipura | Tulatoli Bazar, Raipura, Narsingdi | 23.9993 | 90.8642 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-06 | Expected DG Capacity: 22 KVA
95 | RO-2 | Sylhet | DHK4393 | DHK_G4393 |  | CP+DG | Outdoor GF | Narayanganj | Araihazar | Pancgao,Mollapur,Araihazar,Narayanganj | 23.8075 | 90.6386 |  |  | DITL | ACL |  | Dhaly-Alliance |  | Expected DG Capacity: 22 KVA |  |  | 2026-09-02 | Tempest | 22 | 1000 |  | OK | 17424.33 | 251 | 295 | 44 | OK | Standard | 1. Fuel Pipe - Faulty Note: Injector over fuel pipe fault 2. DG Room Light - Faulty Note: Faulty 3. BTS Room Condition - Faulty Note: DG Room condition bad and poor 4. Fuel Tank - Faulty Note: DG Room fuel not properly kept | Digitized from scanned paper HOTO checklist (Narsingdi zone backfill).
96 | RO-2 | Sylhet | DHK4428 | DHK_X4428 |  | CP+DG | Indoor GF | Kishoreganj | Bhairab | Akbor Nagor, Bharab,thana : Kuliarchar.district : Kishoreganj | 24.1051 | 90.9281 |  |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-03 | Expected DG Capacity: 22 KVA
97 | RO-2 | Sylhet | DHK4606 | DHK_X4606 |  | CP+DG | Indoor GF | Kishoreganj | Kuliarchar | Vill: Jafrabad, P.O: Laxmipur, P.S: Kulairchar, Dist: Kishoreganj | 24.1761 | 90.8594 | No |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-05 | Expected DG Capacity: 22 KVA |  |  | 2026-09-03 | Welland Power | 22 | 2000 |  | OK | 2089 | 244 | 270 | 26 | OK |  | 1,DG Open Space
98 | RO-2 | Sylhet | DHK5181 | DHK_X5181 |  | CP+DG | Outdoor GF | Narsingdi | Narsingdi Sadar | Dilarpur Bazar,Narsingdi Sadar,Narsingdi | 23.8845 | 90.7313 | No |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-07 | Expected DG Capacity: 22 KVA |  |  | 2026-09-03 | Pramac | 22 | 200 |  | OK |  | 365 | 379 | 14 |  |  | 1,DG Air Filter Box Lock Missing, 2,Ari Filter Missing 3,Radiator Muntin Broken 4,Out Door BTS Room Light Faulty
99 | RO-2 | Sylhet | DHK5547 | DHK_X5547 |  | CP+DG | Outdoor GF | Narsingdi | Narsingdi Sadar | Sree Nagar Bazar, Narsingdi Sadar, Narsingdi, Dhaka | 23.8802 | 90.7673 | No |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-07 | Expected DG Capacity: 22 KVA |  |  | 2026-09-03 | Welland Power | 22 | 120 |  | OK |  | 77 | 77
100 | RO-2 | Sylhet | DHK5584 | DHK_X5584 |  | CP+DG | Outdoor GF | Narsingdi | Narsingdi Sadar | Karimpur Bazar,Narsingdi sadar,Narsingdi | 23.8901 | 90.7461 | No |  | DITL | ACL |  | Dhaly-Alliance | 2026-09-06 | Expected DG Capacity: 13 KVA |  |  | 2026-09-03 | Mets | 13 | 1000 |  | OK | 4160.4 | 107.6 | 107.6 |  | OK |  | 1. Site Cleaning Status - Faulty Note: Need Bush Clean

## Full HOTO Checklist
Site Code | District | Thana | HOTO Actual Date | Site Type | BTS Type | Site Sharing | Shared Operator Name | Key Type | Key Status - BTS Room | Key Status - DG Room | Battery Brand | Battery Serial | Battery AH | Engine Serial | ATS Brand | ATS Mode | Last Service Date | Controller Status | Black Smoke Status | DG Battery Charger | ATS Physical & Functional Status | DG Automation (VDTC/RVDTC/Rectifier) per BL Standard | Fuel Preserved at Safe & Appropriate Location | Exhaust Fan / Ventilation Sufficient When Running | Sufficient Water in Radiator & Battery | DG Radiator Condition | DG Battery Condition | DG Runs in Both Auto & Manual Mode | GENSET ON Alarm Functioning Properly | Lub Oil Status (Level & Colour) | DG RH Meter Working Properly | No Parts Missing (if missing, note in snags below) | Earth Connection OK | Mains Fail Alarm | DC Low Alarm | Rectifier Fault Alarm | High Temperature Alarm | Door Open Alarm | DG Run Alarm | DG Failure Alarm | DG Low Fuel Alarm | Tower / Pole Condition | BTS Room Condition | BTS Floor / Roof Condition | Door Condition | Locking Status | Security Gate Condition | Wall Condition | Fire Extinguisher Status | Site Cleaning Status | Grounding Cable to MGB / Tower Leg | Grounding Pit Status | AC Status | ACP (AC Controller) Status | IVS Status | Transformer Status | MDB / PIU / PMS Status | AVR Status | Solar Panel Status | Solar Controller Status | Solar Inverter Status | Solar Infra Status | No. of AC Units | No. of ACP (AC Controllers) | No. of IVS Units | Energy Meter Reading | 2G Battery (Cells + Brand + Rating) | 3G Battery (Cells + Brand + Rating) | TXN Battery (Cells + Brand + Rating) | Solar Net Meter Number | Solar Net Meter Output | Spare Parts (Disconnected Generator)
SYL_X0133 | Sylhet | Companiganj Syl.
SYL_X0082 | Habiganj | Lakhai | 2026-09-07 | RTT | Indoor | No |  |  |  |  | Lucas
SYL_X0589 | Sylhet | Companiganj Syl.
SYL_X0331 | Habiganj | Habiganj Sadar | 2026-09-07 | GFT | Indoor | Yes |  |  |  |  | Lucas
SYL_X0073 | Sylhet | Companiganj Syl. | 2026-08-30 | [5 empty] | Local | Local | Hamko 100Ah | P8199420039 | 100 | 35212u9527765 | Local | Auto |  | OK | OK | OK | OK | OK | NOK | OK | OK | OK | NOK | OK | OK | OK | OK | OK
SYL_X0117 | Habiganj | Lakhai | 2026-09-04 | GFT | Indoor | No |  |  |  |  | Hamko
SYL_X0566 | Habiganj | Lakhai
SYL_X0162 | Sylhet | Companiganj Syl. | 2026-08-30 | [5 empty] | Local | Open space | Hamko | P033wdcd0250 | 100 | Gv51792R | Local | Auto | 2026-08-22 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
SYL_G0585 | Sylhet | Companiganj Syl.
SYL_X0550 | Moulavibazar | Moulavibazar
SYL_X0291 | Habiganj | Bahubal | 2026-09-06 | GFT | Indoor | No |  |  |  |  | Volvo
SYL_X0087 | Sunamganj | Bishwamvarpur | 2026-09-04 | GFT | Outdoor | No | N/A | Local Key | Local | Local | Hamko | PO33WLDB0008 | 100 | GV51790U884143B | Local | Auto | 2026-08-23 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0097 | Moulavibazar | Moulvibazar Sadar | 2026-09-07 | [7 empty] | Hamko |  |  | N844L2216M524 | [18 empty] | Yes
SYL_X0274 | Sunamganj | Bishwamvarpur
SYL_X0065 | Sylhet | Kanaighat
SYL_X0219 | Sylhet | Kanaighat
SYL_X0257 | Moulavibazar | Moulvibazar Sadar | 2026-09-03 |  |  |  |  | Local Key | Abloy | Open space | Volvo | 27MB0579 | 100 | N844L2216M5260 | Local | Auto | 2026-05-08 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0233 | Sylhet | Kanaighat
SYL_X0092 | Moulavibazar | Moulavibazar | 2026-09-07 |  |  |  |  | Local Key |  |  | Volvo |  | 100 |  | Local | Auto |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0613 | Sunamganj | Bishwamvarpur | 2026-08-31 | GFT | Outdoor | No | N/A |  | LOCAL | Local | Hamko | P033WND010086 | 100 | GV51792 | Local | Auto | 2026-05-23 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | NOK | OK | OK
SYL_X0235 | Sylhet | Zakiganj
SYL_X0218 | Sylhet | Kanaighat
SYL_X0020 | Sylhet | Zakiganj
SYL_X0273 | Sylhet | Kanaighat
SYL_X0204 | Sylhet | Gowainghat
SYL_X0200 | Sylhet | Beanibazar
SYL_X0069 | Sunamganj | Jamalganj | 2026-09-01 |  | Indoor | No |  | Local Key | Local | Local | Hamko | P033XFDI0753 | 100 | 3029DF120 | JRC | Auto | 2026-05-29 | OK | NOK | OK | OK | NOK | OK | OK | NOK | NOK | NOK | OK | NOK | NOK | OK | OK | Yes
SYL_X0222 | Habiganj | Chunarughat | 2026-09-05 | GFT | Indoor | No
SYL_X0142 | Sylhet | Beanibazar
SYL_X0118 | Sylhet | Beanibazar
SYL_X0604 | Habiganj | Habiganj Sadar | 2026-09-06 | GFT | Indoor | No |  |  |  |  | Rahimafrooz
SYL_X0483 | Sylhet | Beanibazar
SYL_X0052 | Habiganj | Nabiganj
SYL_X0089 | Sunamganj | Jamalganj | 2026-09-01 | GFT | Outdoor | No | N/A | Local Key | Local | Local | Hamko | P033XEBD0616 | 100 | GN66044U | Local | Auto | 2026-04-30 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | NOK | OK | OK | Yes
SYL_G0420 | Sunamganj | Jamalganj | 2026-09-01 | GF-RT | Indoor | Yes | Grameen Phone | Local Key | Local | Open | Volvo | 3A15VOI12787308 |  | GNG65732U939425V |  |  |  | OK | OK | OK | OK | OK | OK | OK | OK | NOK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0364 | Moulavibazar | Moulvibazar Sadar | 2026-09-03 |  |  |  |  | Local Key | Local | Local | Volvo | 05BB0325 | 100 | DJ32015 | Local | Auto | 2026-07-28 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0062 | Sylhet | Sylhet Sadar
SYL_X0017 | Sylhet | Jaintiapur
SYL_X0075 | Moulavibazar | Juri | 2026-09-02 |  |  |  |  | Local Key |  |  | Hamko | P033WMC60124 | 100 | M84582216m533CK | Local | Auto | 2026-07-23 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0191 | Sunamganj | Sunamganj Sadar | 2026-09-05 | GFT | Indoor | No | N/A | Local Key | Local | Local | Lucas | 4362597 | 80 | HP511090U981933P | Genthe | Auto | 2026-04-30 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | NOK | OK | OK | Yes
SYL_X0002 | Sylhet | Sylhet Sadar
SYL_X0043 | Sunamganj | South Sunamgonj | 2026-08-31 |  | Indoor | No | N/A |  | LOCAL | LOCAL | Hamko | P033WECK0207 | 100 | HP51109U981641P | Local | Auto | 2026-05-24 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | NOK | OK | OK
SYL_X0568 | Sunamganj | Sunamganj Sadar | 2026-08-31 | GFT | Outdoor | Yes | Grameen Phone | Local Key | Local | Local | Hamko | P033WLDB0108 | 100 | GV51790V | Navana | Auto | 2026-03-30 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0077 | Moulavibazar | Rajnagar | 2026-09-01 | GFT | Indoor | No |  | Master Key - Abloy | Solex | Local | Hamko | PO33WJBK0524 | 100 | DJ51279 | Bangla | Auto | 2026-06-28 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes | OK | OK |  |  | OK | OK | OK
SYL_X0242 | Sunamganj | Sunamganj Sadar | 2026-09-02 | GF-RT | Indoor | No | N/A | Local Key | Local | Local | Hamko | P033XJBJ0375 | 100 | HP35203U912565P | Galaxy | Auto | 2026-06-24 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0213 | Moulavibazar | Barlekha | 2026-09-03 |  |  |  |  | Master Key - Abloy | Local | Abloy | Hamko | P033WECK0148 | 100 | N844L2216N533CK | Local | Auto | 2026-03-31 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0141 | Moulavibazar | Barlekha | 2026-09-02 |  |  |  |  | Master Key - Abloy | ODC | Open space | Hamko | B1H248803G45 |  | N84462216M5260
SYL_X0615 | Moulavibazar | Kulaura | 2026-09-02 |  |  |  |  | Master Key - Abloy | ODC | Open space | Hamko | P033XJBJ0052 | 100 | N844L2216N5330 | Local | Auto | 2026-07-25 | [15 empty] | Yes
SYL_X0611 | Sunamganj | Dowarabazar | 2026-09-02 | GFT | Outdoor | No | N/A | Local Key | Open | Open | Hamko | P033WIDE0636 | 100 | DJ32015*S009835C | Local | Auto | 2026-03-22 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0405 | Sylhet | Kanaighat
SYL_X0247 | Sunamganj | Dowarabazar | 2026-09-02 | GFT | Indoor | Yes | Grameen Phone | Local Key | Local | Local | Hamko | VIMP8188040007 | 100 | SK66045U505120 | Local | Auto | 2026-03-31 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0086 | Sunamganj | Dowarabazar | 2026-09-02 | GFT | Outdoor | Yes | Robi | Local Key | 00 | Open | Lucas | 3AI5VY12787359 | 100 | HP51109V983311P | Local | Auto | 2026-07-31 | OK | OK | OK | OK | OK | OK | OK | OK | NOK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0067 | Moulavibazar | Kulaura | 2026-08-31 | [5 empty] | Abloy | Solex | Volvo | 25JB0612 | 100 | DJ320155009844C | Bangla | Auto | 2026-05-21 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | NOK | OK | OK | Yes
SYL_X0103 | Moulavibazar | Kulaura | 2026-09-02 |  |  |  |  | Master Key - Abloy | Abloy | Abloy | Spark | 3J06AL11015303 | 80 | N8431496N52001 | Local | Auto | 2026-06-18 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
SYL_X0105 | Moulavibazar | Kamalganj | 2026-09-03 |  |  |  |  | Master Key - Abloy | Abloy | Abloy | Rahim Afroz | 328TA12749902 | 100 | N844L2216M5260 | Local | Auto | 2026-08-15 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0093 | Sylhet | Gowainghat
SYL_X0537 | Sylhet | Balaganj
SYL_X0543 | Sunamganj | Dowarabazar | 2026-09-02 | GFT | Outdoor | No | N/A | Local Key | Local Key | Open | Hamko | P033XFOF0145 | 100 | GN65732U984108T | Tempest | Auto | 2026-06-27 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0426 | Sylhet | Fenchuganj
SYL_X0083 | Habiganj | Ajmiriganj | 2026-09-07 | GFT | Outdoor | Yes |  |  |  |  | Lucas |  | 100 |  | Local | Auto | [16 empty] | Yes
SYL_G0397 | Sunamganj | Tahirpur | 2026-09-04 | GFT | Outdoor | Yes | Grameen Phone | Local Key | Local | Open | Hamko | PW33WEDD0060 | 100 | GU51792R | Local | Auto | 2026-02-17 | OK | NOK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | NOK | OK | OK | Yes
SYL_X0072 | Habiganj | Baniachong | 2026-09-04 | GFT | Indoor | No |  |  |  |  | Volvo
SYL_G0422 | Sunamganj | Tahirpur | 2026-09-06 | GFT | Outdoor | Yes | Grameen Phone | Local Key | Local | Local | Hamko | P033XHBK0641 | 100 | HP35203U935011S | Local | Auto |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0156 | Sunamganj | Chhatak | 2026-09-02 | GFT | Outdoor | No | N/A | Local Key | Local | Local | Hamko | P033WIDE0634 | 100 | JV51790U983071B | LOCAL | Auto | 2026-04-26 | OK | OK | OK | OK | OK | OK | OK | OK | NOK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0152 | Sunamganj | Tahirpur | 2026-09-04 | GFT | Indoor | No | N/A | Local Key | Local | Local | 100 | 12787308 | 100 | GN5732U939425V | Local | Auto | 2026-08-30 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
SYL_X0221 | Sunamganj | South Sunamgonj | 2026-09-05 | GFT | Indoor | No | N/A | Local Key | Local | Local | Hamko | V1H24880705 | 100 | DJ32015-S0099220 | Ghaddar | Auto | 2026-04-30 | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK |  | OK | OK | Yes
SYL_X0554 | Sunamganj | Derai | 2026-09-03 | GFT | Indoor | Yes | Grameen Phone | Local Key | Local | Local | 100 | P033WECK0045 | 100 | GN65750U9457745 | Local | Auto | 2026-06-21 | OK | NOK | OK | OK | OK | NOK | OK | OK | OK | OK | OK | OK | NOK | OK | OK | Yes
SYL_X0091 | Sunamganj | Sullah | 2026-09-03 |  | Indoor | No | N/A | Local Key | Local | Local | Hamko | P033XFDF0162 | 100 | GN66044U | Local | Auto | 2026-06-22 | OK | OK | OK | OK | OK | OK | OK | OK | NOK | OK | OK | OK | NOK | OK | OK | Yes | [24 empty] | OK
DHK_X0210 | Narsingdi | Raipura
DHK_X0213 | Narsingdi | Narsingdi Sadar | 2026-08-17 | [7 empty] | Hamko |  | 100 |  |  | Auto | 2026-08-17
DHK_X0231 | Kishoreganj | Bhairab
DHK_X0750 | Narsingdi | Palash | 2026-09-02 | [7 empty] | Spark |  | 100 |  |  | Auto | 2026-03-27
DHK_X1097 | Narsingdi | Narsingdi Sadar | 2026-09-01 | [9 empty] | 160 |  |  | Auto
DHK_X1171 | Narsingdi | Raipura
DHK_X1648 | Narsingdi | Shibpur
DHK_X1669 | Kishoreganj | Kuliarchar
DHK_X1674 | Narsingdi | Shibpur
DHK_X1801 | Narsingdi | Narsingdi Sadar | 2026-09-01 | [9 empty] | 100 |  |  | Auto
DHK_X1805 | Narsingdi | Narsingdi Sadar | 2026-09-01 | [9 empty] | 100 |  |  | Auto
DHK_X1806 | Kishoreganj | Bhairab
DHK_X1879 | Narsingdi | Shibpur | 2026-09-01 | [7 empty] | Navana |  | 100 |  |  | Auto | 2026-06-30
DHK_X1914 | Narsingdi | Manohardi | 2026-09-01 | [7 empty] | Spark |  | 100 | B17C103882 |  | Auto
DHK_X1925 | Narsingdi | Shibpur | 2026-09-01 | [7 empty] | Hamko |  | 100 | UK-28654-9002904 |  | Auto
DHK_X2063 | Narsingdi | Shibpur
DHK_X2119 | Narsingdi | Raipura
DHK_X2551 | Narsingdi | Belabo
DHK_X2655 | Kishoreganj | Bhairab
DHK_X2656 | Kishoreganj | Kuliarchar
DHK_X2681 | Narsingdi | Narsingdi Sadar | 2026-08-31 | [9 empty] | 100 |  |  | Auto | 2026-03-31
DHK_X2727 | Narayanganj | Araihazar | 2026-09-02 | [9 empty] | 100 |  |  | Auto | 2026-08-17
DHK_X2941 | Narsingdi | Belabo
DHK_X3450 | Kishoreganj | Bhairab
DHK_X3451 | Narsingdi | Shibpur | 2026-09-01 | [7 empty] | Hamko |  | 100 | GN66044U2087668 | Energis | Auto | 2026-08-15
DHK_X3470 | Narsingdi | Raipura
DHK_G4393 | Narayanganj | Araihazar | 2026-09-02 | [7 empty] | Lucas |  | 100 |  | Mets Energy | Auto | 2026-06-19
DHK_X4428 | Kishoreganj | Bhairab
DHK_X4606 | Kishoreganj | Kuliarchar | 2026-09-03 | GF-RT | Outdoor |  |  | Local Key |  | Local | Hamko | PO33WLAG0107 |  | UK255709001977 | Narada | Auto |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
DHK_X5181 | Narsingdi | Narsingdi Sadar | 2026-09-03 |  |  |  |  | Local Key |  | Local | [5 empty] | Auto |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
DHK_X5547 | Narsingdi | Narsingdi Sadar | 2026-09-03 | GF-RT | Indoor |  |  | Local Key |  | Local | Spark | 3A04VM11356448 | 100 A | VK32046-9003859 |  | Auto |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes
DHK_X5584 | Narsingdi | Narsingdi Sadar | 2026-09-03 | GF-RT | Outdoor |  |  | Local Key |  |  | Hamko | P033XGDJ0848 | 100 | LD6282393 |  | Auto |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Yes | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | NA | NOK

## Cumulative Update
| 79 | 57
Date | Target | Done | Cum Target | Cum Done
2026-08-30 | 2 | 2 | 2 | 2
2026-08-31 | 0 | 5 | 2 | 7
2026-09-01 | 0 | 11 | 2 | 18
2026-09-02 | 2 | 13 | 4 | 31
2026-09-03 | 10 | 10 | 14 | 41
2026-09-04 | 0 | 5 | 14 | 46
2026-09-05 | 10 | 3 | 24 | 49
2026-09-06 | 10 | 3 | 34 | 52
2026-09-07 | 8 | 5 | 42 | 57
2026-09-08 | 4 | 0 | 46 | 57
2026-09-09 | 6 | 0 | 52 | 57
2026-09-10 | 6 | 0 | 58 | 57
2026-09-11 | 0 | 0 | 58 | 57
2026-09-12 | 4 | 0 | 62 | 57
2026-09-13 | 3 | 0 | 65 | 57
2026-09-14 | 3 | 0 | 68 | 57
2026-09-15 | 3 | 0 | 71 | 57
2026-09-16 | 3 | 0 | 74 | 57
2026-09-17 | 3 | 0 | 77 | 57
2026-09-18 | 0 | 0 | 77 | 57
2026-09-19 | 2 | 0 | 79 | 57

## DG Brand Mismatch
Site Code | District | Thana | Expected DG Brand (Banglalink Record) | Actual DG Brand (Field Found) | HOTO Actual Date
SYL_X0073 | Sylhet | Companiganj Syl. | Ghaddar | Fg wilson | 2026-08-30
SYL_X0089 | Sunamganj | Jamalganj | Pramac | Tempest | 2026-09-01
SYL_X0191 | Sunamganj | Sunamganj Sadar | Gentec | FG Wilson | 2026-09-05
SYL_X0568 | Sunamganj | Sunamganj Sadar | Pramac | Welland Power | 2026-08-31
SYL_X0213 | Moulavibazar | Barlekha | Pramac | FG Wilson | 2026-09-03
SYL_X0611 | Sunamganj | Dowarabazar | Pramac | FG Wilson | 2026-09-02
SYL_X0083 | Habiganj | Ajmiriganj | Mets | FG Wilson | 2026-09-07
SYL_G0397 | Sunamganj | Tahirpur | FG Wilson | Mets | 2026-09-04
SYL_X0072 | Habiganj | Baniachong | Onis Visa | Welland Power | 2026-09-04
SYL_X0152 | Sunamganj | Tahirpur | Mets | Tempest | 2026-09-04
SYL_X0091 | Sunamganj | Sullah | Gentec | Tempest | 2026-09-03

## Fuel Summary
Site Code | District | Thana | HOTO Date | Tank Capacity (Ltr) | Fuel w/ Sediment (Ltr) | Fuel incl. Impurity (Ltr) | Impurity/Water (Ltr)
SYL_X0083 | Habiganj | Ajmiriganj | 2026-09-07 | 2000 | 386 | 431 | 45
SYL_X0291 | Habiganj | Bahubal | 2026-09-06 | 2000 | 379 | 394 | 15
SYL_X0072 | Habiganj | Baniachong | 2026-09-04 | 2000 | 295 | 295
SYL_X0222 | Habiganj | Chunarughat | 2026-09-05 | 2000 | 345 | 345 | 00
SYL_X0331 | Habiganj | Habiganj Sadar | 2026-09-07 | 1000 | 195 | 245 | 50
SYL_X0604 | Habiganj | Habiganj Sadar | 2026-09-06 | 2000 | 163 | 163
SYL_X0082 | Habiganj | Lakhai | 2026-09-07 | 2000 | 386 | 431 | 45
SYL_X0117 | Habiganj | Lakhai | 2026-09-04 | 2000 | 250 | 250
| Subtotal: Habiganj |  |  |  | 2399 | 2554 | 155
DHK_X4606 | Kishoreganj | Kuliarchar | 2026-09-03 | 2000 | 244 | 270 | 26
| Subtotal: Kishoreganj |  |  |  | 244 | 270 | 26
SYL_X0141 | Moulavibazar | Barlekha | 2026-09-02 | 2000 | 245 | 225 | 20
SYL_X0213 | Moulavibazar | Barlekha | 2026-09-03 | 2000 | 290 | 312 | 22
SYL_X0075 | Moulavibazar | Juri | 2026-09-02 | 2000 | 230 | 230 | 00
SYL_X0105 | Moulavibazar | Kamalganj | 2026-09-03 | 1000 | 248 | 248
SYL_X0067 | Moulavibazar | Kulaura | 2026-08-31 | 2000 | 372 | 372
SYL_X0103 | Moulavibazar | Kulaura | 2026-09-02 | 2000 | 354 | 354
SYL_X0615 | Moulavibazar | Kulaura | 2026-09-02 | 2000 | 282 | 297 | 12
SYL_X0092 | Moulavibazar | Moulavibazar | 2026-09-07 | 2000 | 315 | 315
SYL_X0097 | Moulavibazar | Moulvibazar Sadar | 2026-09-07 | 65 | 63 | 63
SYL_X0257 | Moulavibazar | Moulvibazar Sadar | 2026-09-03 | 2000 | 223 | 223
SYL_X0364 | Moulavibazar | Moulvibazar Sadar | 2026-09-03 | 2000 | 394 | 394 | 00
SYL_X0077 | Moulavibazar | Rajnagar | 2026-09-01 | 2000 |  | 327
| Subtotal: Moulavibazar |  |  |  | 3016 | 3360 | 54
DHK_G4393 | Narayanganj | Araihazar | 2026-09-02 | 1000 | 251 | 295 | 44
DHK_X2727 | Narayanganj | Araihazar | 2026-09-02 | 2000 | 293 | 327 | 34
| Subtotal: Narayanganj |  |  |  | 544 | 622 | 78
DHK_X1914 | Narsingdi | Manohardi | 2026-09-01 | 2000 | 263 | 285 | 22
DHK_X0213 | Narsingdi | Narsingdi Sadar | 2026-08-17 | 2000 | 179 | 253 | 74
DHK_X1097 | Narsingdi | Narsingdi Sadar | 2026-09-01 | 2000 | 183 | 183
DHK_X1801 | Narsingdi | Narsingdi Sadar | 2026-09-01 |  | 253 | 253
DHK_X1805 | Narsingdi | Narsingdi Sadar | 2026-09-01 |  | 338 | 380 | 42
DHK_X2681 | Narsingdi | Narsingdi Sadar | 2026-08-31 | 2000 | 419 | 419
DHK_X5181 | Narsingdi | Narsingdi Sadar | 2026-09-03 | 200 | 365 | 379 | 14
DHK_X5547 | Narsingdi | Narsingdi Sadar | 2026-09-03 | 120 | 77 | 77
DHK_X5584 | Narsingdi | Narsingdi Sadar | 2026-09-03 | 1000 | 107.6 | 107.6
DHK_X0750 | Narsingdi | Palash | 2026-09-02 | 2000 | 296.1 | 328 | 31.9
DHK_X1879 | Narsingdi | Shibpur | 2026-09-01 | 1000 | 206.2 | 236 | 29.8
DHK_X1925 | Narsingdi | Shibpur | 2026-09-01 | 2000 | 261 | 305 | 44
DHK_X3451 | Narsingdi | Shibpur | 2026-09-01 | 2000 | 285.6 | 290 | 4.4
| Subtotal: Narsingdi |  |  |  | 3233.5 | 3495.6 | 262.1
SYL_X0087 | Sunamganj | Bishwamvarpur | 2026-09-04 | 2000 | 212 | 212
SYL_X0613 | Sunamganj | Bishwamvarpur | 2026-08-31 | 2000 | 134 | 149 | 15
SYL_X0156 | Sunamganj | Chhatak | 2026-09-02 | 800 | 245 | 245
SYL_X0554 | Sunamganj | Derai | 2026-09-03 | 1000 | 110 | 144 | 34
SYL_X0086 | Sunamganj | Dowarabazar | 2026-09-02 | 850 | 163 | 179 | 16
SYL_X0247 | Sunamganj | Dowarabazar | 2026-09-02 | 2000 | 352 | 352
SYL_X0543 | Sunamganj | Dowarabazar | 2026-09-02 | 2000 | 171 | 297 | 171
SYL_X0611 | Sunamganj | Dowarabazar | 2026-09-02 | 850 | 66 | 122 | 56
SYL_G0420 | Sunamganj | Jamalganj | 2026-09-01 | 2000 | 178 | 297 | 119
SYL_X0069 | Sunamganj | Jamalganj | 2026-09-01 | 2000 | 55 | 114 | 59
SYL_X0089 | Sunamganj | Jamalganj | 2026-09-01 | 2000 | 104 | 104
SYL_X0043 | Sunamganj | South Sunamgonj | 2026-08-31 | 2000 | 149 | 186 | 37
SYL_X0221 | Sunamganj | South Sunamgonj | 2026-09-05 | 2000 | 189 | 256 | 67
SYL_X0091 | Sunamganj | Sullah | 2026-09-03 | 2000 | 118 | 157 | 39
SYL_X0191 | Sunamganj | Sunamganj Sadar | 2026-09-05 | 2000 | 241 | 241
SYL_X0242 | Sunamganj | Sunamganj Sadar | 2026-09-02 | 2000 | 104 | 104
SYL_X0568 | Sunamganj | Sunamganj Sadar | 2026-08-31 | 2000 | 282 | 297 | 15
SYL_G0397 | Sunamganj | Tahirpur | 2026-09-04 | 2000 | 124 | 124
SYL_G0422 | Sunamganj | Tahirpur | 2026-09-06 | 2000 | 277 | 369 | 90
SYL_X0152 | Sunamganj | Tahirpur | 2026-09-04 | 2000 | 197 | 197
| Subtotal: Sunamganj |  |  |  | 3471 | 4146 | 718
SYL_X0073 | Sylhet | Companiganj Syl. | 2026-08-30 | 2000 | 14 | 14 | 00
SYL_X0162 | Sylhet | Companiganj Syl. | 2026-08-30 | 2000 | 223 | 223 | 00
| Subtotal: Sylhet |  |  |  | 237 | 237 | 0
| GRAND TOTAL |  |  |  | 13144.5 | 14684.6 | 1293.1

## HOTO Plan (Gantt)
Site Code | District | Thana | Assigned To | Phase | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19
SYL_X0083 | Habiganj | Ajmiriganj | Md. Ismail Hossain | P1 | bar: 2026-09-07
SYL_X0291 | Habiganj | Bahubal | Md. Ismail Hossain | P1 | bar: 2026-09-06
SYL_X0072 | Habiganj | Baniachong | Md. Ismail Hossain | P1 | bar: 2026-09-04
SYL_X0222 | Habiganj | Chunarughat | Md. Ismail Hossain | P1 | bar: 2026-09-05
SYL_X0331 | Habiganj | Habiganj Sadar | Md. Ismail Hossain | P1 | bar: 2026-09-07
SYL_X0604 | Habiganj | Habiganj Sadar | Md. Ismail Hossain | P1 | bar: 2026-09-06
SYL_X0082 | Habiganj | Lakhai | Md. Ismail Hossain | P1 | bar: 2026-09-07
SYL_X0117 | Habiganj | Lakhai | Md. Ismail Hossain | P1 | bar: 2026-09-04
SYL_X0566 | Habiganj | Lakhai | Md. Ismail Hossain | P1 | 2026-09-05: 566
SYL_X0052 | Habiganj | Nabiganj | Md. Ismail Hossain | P1 | 2026-09-06: 052
DHK_X0231 | Kishoreganj | Bhairab | Md. Mahabur Rahman | P1 | 2026-09-03: 231
DHK_X1806 | Kishoreganj | Bhairab | Mosharof | P1 | 2026-09-02: 806
DHK_X2655 | Kishoreganj | Bhairab | Md. Mahabur Rahman | P1 | 2026-09-03: 655
DHK_X3450 | Kishoreganj | Bhairab | Mosharof | P1 | 2026-09-02: 450
DHK_X4428 | Kishoreganj | Bhairab | Md. Mahabur Rahman | P1 | 2026-09-03: 428
DHK_X1669 | Kishoreganj | Kuliarchar | Md. Mahabur Rahman | P1 | 2026-09-05: 669
DHK_X2656 | Kishoreganj | Kuliarchar | Mosharof | P1 | 2026-09-03: 656
DHK_X4606 | Kishoreganj | Kuliarchar | Md. Mahabur Rahman | P1 | bar: 2026-09-03
SYL_X0141 | Moulavibazar | Barlekha | Sourav Sarkar | P1 | bar: 2026-09-02
SYL_X0213 | Moulavibazar | Barlekha | Sourav Sarkar | P1 | bar: 2026-09-03
SYL_X0075 | Moulavibazar | Juri | Sourav Sarkar | P1 | bar: 2026-09-02
SYL_X0105 | Moulavibazar | Kamalganj | Sourav Sarkar | P1 | bar: 2026-09-03
SYL_X0067 | Moulavibazar | Kulaura | Sourav Sarkar | P1 | bar: 2026-08-31
SYL_X0103 | Moulavibazar | Kulaura | Sourav Sarkar | P1 | bar: 2026-09-02
SYL_X0615 | Moulavibazar | Kulaura | Sourav Sarkar | P1 | bar: 2026-09-02
SYL_X0092 | Moulavibazar | Moulavibazar | Sourav Sarkar | P1 | bar: 2026-09-07
SYL_X0550 | Moulavibazar | Moulavibazar | Sourav Sarkar | P1 | 2026-09-07: 550
SYL_X0097 | Moulavibazar | Moulvibazar Sadar | Sourav Sarkar | P1 | bar: 2026-09-07
SYL_X0257 | Moulavibazar | Moulvibazar Sadar | Sourav Sarkar | P1 | bar: 2026-09-03
SYL_X0364 | Moulavibazar | Moulvibazar Sadar | Sourav Sarkar | P1 | bar: 2026-09-03
SYL_X0077 | Moulavibazar | Rajnagar | Sourav Sarkar | P1 | bar: 2026-09-01
DHK_G4393 | Narayanganj | Araihazar | Md. Mahabur Rahman | P1 | bar: 2026-09-02
DHK_X2727 | Narayanganj | Araihazar | Md. Mahabur Rahman | P1 | bar: 2026-09-02
DHK_X2551 | Narsingdi | Belabo | Mosharof | P1 | 2026-09-03: 551
DHK_X2941 | Narsingdi | Belabo | Mosharof | P1 | 2026-09-06: 941
DHK_X1914 | Narsingdi | Manohardi | Md. Mahabur Rahman | P1 | bar: 2026-09-01
DHK_X0213 | Narsingdi | Narsingdi Sadar | Mosharof | P1 | bar: 2026-08-17
DHK_X1097 | Narsingdi | Narsingdi Sadar | Mosharof | P1 | bar: 2026-09-01
DHK_X1801 | Narsingdi | Narsingdi Sadar | Mosharof | P1 | bar: 2026-09-01
DHK_X1805 | Narsingdi | Narsingdi Sadar | Mosharof | P1 | bar: 2026-09-01
DHK_X2681 | Narsingdi | Narsingdi Sadar | Md. Mahabur Rahman | P1 | bar: 2026-08-31
DHK_X5181 | Narsingdi | Narsingdi Sadar | Md. Mahabur Rahman | P1 | bar: 2026-09-03
DHK_X5547 | Narsingdi | Narsingdi Sadar | Md. Mahabur Rahman | P1 | bar: 2026-09-03
DHK_X5584 | Narsingdi | Narsingdi Sadar | Mosharof | P1 | bar: 2026-09-03
DHK_X0750 | Narsingdi | Palash | Md. Mahabur Rahman | P1 | bar: 2026-09-02
DHK_X0210 | Narsingdi | Raipura | Md. Mahabur Rahman | P1 | 2026-09-05: 210
DHK_X1171 | Narsingdi | Raipura | Mosharof | P1 | 2026-09-05: 171
DHK_X2119 | Narsingdi | Raipura | Md. Mahabur Rahman | P1 | 2026-09-06: 119
DHK_X3470 | Narsingdi | Raipura | Md. Mahabur Rahman | P1 | 2026-09-06: 470
DHK_X1648 | Narsingdi | Shibpur | Mosharof | P1 | 2026-09-05: 648
DHK_X1674 | Narsingdi | Shibpur | Md. Mahabur Rahman | P1 | 2026-09-06: 674
DHK_X1879 | Narsingdi | Shibpur | Md. Mahabur Rahman | P1 | bar: 2026-09-01
DHK_X1925 | Narsingdi | Shibpur | Md. Mahabur Rahman | P1 | bar: 2026-09-01
DHK_X2063 | Narsingdi | Shibpur | Md. Mahabur Rahman | P1 | 2026-09-07: 063
DHK_X3451 | Narsingdi | Shibpur | Md. Mahabur Rahman | P1 | bar: 2026-09-01
SYL_X0087 | Sunamganj | Bishwamvarpur | Md. Ismail Hossain | P1 | bar: 2026-09-04
SYL_X0274 | Sunamganj | Bishwamvarpur | Md. Ismail Hossain | P1 | 2026-09-07: 274
SYL_X0613 | Sunamganj | Bishwamvarpur | Md. Ismail Hossain | P1 | bar: 2026-08-31
SYL_X0156 | Sunamganj | Chhatak | Md. Ismail Hossain | P1 | bar: 2026-09-02
SYL_X0554 | Sunamganj | Derai | Md. Ismail Hossain | P1 | bar: 2026-09-03
SYL_X0086 | Sunamganj | Dowarabazar | Md. Ismail Hossain | P1 | bar: 2026-09-02
SYL_X0247 | Sunamganj | Dowarabazar | Md. Ismail Hossain | P1 | bar: 2026-09-02
SYL_X0543 | Sunamganj | Dowarabazar | Md. Ismail Hossain | P1 | bar: 2026-09-02
SYL_X0611 | Sunamganj | Dowarabazar | Md. Ismail Hossain | P1 | bar: 2026-09-02
SYL_G0420 | Sunamganj | Jamalganj | Md. Ismail Hossain | P1 | bar: 2026-09-01
SYL_X0069 | Sunamganj | Jamalganj | Md. Ismail Hossain | P1 | bar: 2026-09-01
SYL_X0089 | Sunamganj | Jamalganj | Md. Ismail Hossain | P1 | bar: 2026-09-01
SYL_X0043 | Sunamganj | South Sunamgonj | Md. Ismail Hossain | P1 | bar: 2026-08-31
SYL_X0221 | Sunamganj | South Sunamgonj | Md. Ismail Hossain | P1 | bar: 2026-09-05
SYL_X0091 | Sunamganj | Sullah | Md. Ismail Hossain | P1 | bar: 2026-09-03
SYL_X0191 | Sunamganj | Sunamganj Sadar | Md. Ismail Hossain | P1 | bar: 2026-09-05
SYL_X0242 | Sunamganj | Sunamganj Sadar | Md. Ismail Hossain | P1 | bar: 2026-09-02
SYL_X0568 | Sunamganj | Sunamganj Sadar | Md. Ismail Hossain | P1 | bar: 2026-08-31
SYL_G0397 | Sunamganj | Tahirpur | Md. Ismail Hossain | P1 | bar: 2026-09-04
SYL_G0422 | Sunamganj | Tahirpur | Md. Ismail Hossain | P1 | bar: 2026-09-06
SYL_X0152 | Sunamganj | Tahirpur | Md. Ismail Hossain | P1 | bar: 2026-09-04
SYL_X0537 | Sylhet | Balaganj | Md. Ismail Hossain | P1 | 2026-09-10: 537
SYL_X0118 | Sylhet | Beanibazar | Md. Ismail Hossain | P1 | 2026-09-19: 118
SYL_X0142 | Sylhet | Beanibazar | Md. Ismail Hossain | P1 | 2026-09-17: 142
SYL_X0200 | Sylhet | Beanibazar | Md. Ismail Hossain | P1 | 2026-09-17: 200
SYL_X0483 | Sylhet | Beanibazar | Md. Ismail Hossain | P1 | 2026-09-17: 483
SYL_G0585 | Sylhet | Companiganj Syl. | Md. Ismail Hossain | P1 | 2026-09-13: 585
SYL_X0073 | Sylhet | Companiganj Syl. | Md. Ismail Hossain | P1 | bar: 2026-08-30
SYL_X0133 | Sylhet | Companiganj Syl. | Md. Ismail Hossain | P1 | 2026-09-12: 133
SYL_X0162 | Sylhet | Companiganj Syl. | Md. Ismail Hossain | P1 | bar: 2026-08-30
SYL_X0589 | Sylhet | Companiganj Syl. | Md. Ismail Hossain | P1 | 2026-09-12: 589
SYL_X0426 | Sylhet | Fenchuganj | Md. Ismail Hossain | P1 | 2026-09-19: 426
SYL_X0093 | Sylhet | Gowainghat | Md. Ismail Hossain | P1 | 2026-09-13: 093
SYL_X0204 | Sylhet | Gowainghat | Md. Ismail Hossain | P1 | 2026-09-13: 204
SYL_X0017 | Sylhet | Jaintiapur | Md. Ismail Hossain | P1 | 2026-09-14: 017
SYL_X0065 | Sylhet | Kanaighat | Md. Ismail Hossain | P1 | 2026-09-14: 065
SYL_X0218 | Sylhet | Kanaighat | Md. Ismail Hossain | P1 | 2026-09-16: 218
SYL_X0219 | Sylhet | Kanaighat | Md. Ismail Hossain | P1 | 2026-09-15: 219
SYL_X0233 | Sylhet | Kanaighat | Md. Ismail Hossain | P1 | 2026-09-14: 233
SYL_X0273 | Sylhet | Kanaighat | Md. Ismail Hossain | P1 | 2026-09-16: 273
SYL_X0405 | Sylhet | Kanaighat | Md. Ismail Hossain | P1 | 2026-09-16: 405
SYL_X0002 | Sylhet | Sylhet Sadar | Md. Ismail Hossain | P1 | 2026-09-10: 002
SYL_X0062 | Sylhet | Sylhet Sadar | Md. Ismail Hossain | P1 | 2026-09-12: 062
SYL_X0020 | Sylhet | Zakiganj | Md. Ismail Hossain | P1 | 2026-09-15: 020
SYL_X0235 | Sylhet | Zakiganj | Md. Ismail Hossain | P1 | 2026-09-15: 235

## Snag Report
Site Code | District | Thana | Snag # | System | Component | Status Found | Observations | Action Status | Logged
DHK_G4393 | 4 snag(s), 4 open
DHK_G4393 | Narayanganj | Araihazar | S-034 | DG | Fuel Pipe | Faulty | Injector over fuel pipe fault | Open | 03-Sep-26
DHK_G4393 | Narayanganj | Araihazar | S-035 | DG | DG Room Light | Faulty | Faulty | Open | 03-Sep-26
DHK_G4393 | Narayanganj | Araihazar | S-036 | DG | BTS Room Condition | Faulty | DG Room condition bad and poor | Open | 03-Sep-26
DHK_G4393 | Narayanganj | Araihazar | S-037 | DG | Fuel Tank | Faulty | DG Room fuel not properly kept | Open | 03-Sep-26
DHK_X0750 | 3 snag(s), 3 open
DHK_X0750 | Narsingdi | Palash | S-023 | DG | DG Room Light | Faulty | Faulty | Open | 03-Sep-26
DHK_X0750 | Narsingdi | Palash | S-024 | DG | Canopy | Faulty | One part canopy open | Open | 03-Sep-26
DHK_X0750 | Narsingdi | Palash | S-025 | DG | Controller Sensor | Faulty | DG Controller box open | Open | 03-Sep-26
DHK_X1801 | 1 snag(s), 1 open
DHK_X1801 | Narsingdi | Narsingdi Sadar | S-026 | DG | Controller Sensor | Faulty | DG Controller condition very poor | Open | 03-Sep-26
DHK_X1805 | 1 snag(s), 1 open
DHK_X1805 | Narsingdi | Narsingdi Sadar | S-027 | DG | Controller Sensor | Faulty | DG Controller Box faulty | Open | 03-Sep-26
DHK_X1879 | 2 snag(s), 2 open
DHK_X1879 | Narsingdi | Shibpur | S-038 | DG | BTS Room Condition | Faulty | DG Room condition very poor | Open | 03-Sep-26
DHK_X1879 | Narsingdi | Shibpur | S-039 | DG | Radiator | Faulty | DG condition poor - need radiator mounting | Open | 03-Sep-26
DHK_X1914 | 3 snag(s), 3 open
DHK_X1914 | Narsingdi | Manohardi | S-028 | DG | BTS Room Condition | Faulty | DG Room condition very poor | Open | 03-Sep-26
DHK_X1914 | Narsingdi | Manohardi | S-029 | DG | DG Room Light | Faulty | Faulty | Open | 03-Sep-26
DHK_X1914 | Narsingdi | Manohardi | S-030 | DG | Fuel Tank Lock System | Faulty | Faulty | Open | 03-Sep-26
DHK_X2727 | 3 snag(s), 3 open
DHK_X2727 | Narayanganj | Araihazar | S-031 | DG | Radiator | Faulty | DG Radiator mounting broken | Open | 03-Sep-26
DHK_X2727 | Narayanganj | Araihazar | S-032 | DG | Genset Alarm | Faulty | DG Run Alarm probably needs wiring | Open | 03-Sep-26
DHK_X2727 | Narayanganj | Araihazar | S-033 | DG | DG Room Light | Faulty | DG Room wiring faulty | Open | 03-Sep-26
DHK_X5584 | 1 snag(s), 1 open
DHK_X5584 | Narsingdi | Narsingdi Sadar | S-052 | General | Site Cleaning Status | Faulty | Need Bush Clean | Open | 04-Sep-26
SYL_G0397 | 5 snag(s), 5 open
SYL_G0397 | Sunamganj | Tahirpur | S-055 | DG | DG lube oil empty | Faulty |  | Open | 04-Sep-26
SYL_G0397 | Sunamganj | Tahirpur | S-056 | DG | servicing date run hour over | Faulty |  | Open | 04-Sep-26
SYL_G0397 | Sunamganj | Tahirpur | S-057 | DG | Font site canopy missing | Faulty |  | Open | 04-Sep-26
SYL_G0397 | Sunamganj | Tahirpur | S-058 | DG | DG back site canopy missing | Faulty | Charging dynamo faulty | Open | 04-Sep-26
SYL_G0397 | Sunamganj | Tahirpur | S-059 | DG | Need to overhaling | Faulty |  | Open | 04-Sep-26
SYL_G0420 | 1 snag(s), 1 open
SYL_G0420 | Sunamganj | Jamalganj | S-009 | DG | Radiator fully block dust | Faulty |  | Open | 03-Sep-26
SYL_G0422 | 1 snag(s), 1 open
SYL_G0422 | Sunamganj | Tahirpur | S-064 | DG | No servicing date found. | Faulty |  | Open | 06-Sep-26
SYL_X0043 | 1 snag(s), 1 open
SYL_X0043 | Sunamganj | South Sunamgonj | S-001 | DG | DG Fan Belt Loose | Faulty | 1) Dg fan belt loss 2)charging dynamo properly not setting 3) engine lube oil shortest | Open | 31-Aug-26
SYL_X0082 | 1 snag(s), 1 open
SYL_X0082 | Habiganj | Lakhai | S-071 | DG | DG Dynamo faulty | Faulty |  | Open | 07-Sep-26
SYL_X0086 | 2 snag(s), 2 open
SYL_X0086 | Sunamganj | Dowarabazar | S-017 | DG | DG fan bet losse | Faulty |  | Open | 03-Sep-26
SYL_X0086 | Sunamganj | Dowarabazar | S-018 | DG | Radiator s blocked with dust. | Faulty |  | Open | 03-Sep-26
SYL_X0089 | 1 snag(s), 1 open
SYL_X0089 | Sunamganj | Jamalganj | S-008 | DG | Over Run | Faulty |  | Open | 03-Sep-26
SYL_X0091 | 4 snag(s), 4 open
SYL_X0091 | Sunamganj | Sullah | S-043 | DG | DG controller display not visible | Faulty |  | Open | 03-Sep-26
SYL_X0091 | Sunamganj | Sullah | S-044 | DG | The radiator is full of dust | Faulty |  | Open | 03-Sep-26
SYL_X0091 | Sunamganj | Sullah | S-045 | DG | Lube oil level is low | Faulty |  | Open | 03-Sep-26
SYL_X0091 | Sunamganj | Sullah | S-046 | General | (unspecified) | Faulty | The tin sheets on the site's roof are damaged, and the brickwork on one side has collapsed; the wall needs to be repaired. | Open | 03-Sep-26
SYL_X0092 | 2 snag(s), 2 open
SYL_X0092 | Moulavibazar | Moulavibazar | S-065 | DG | Fuel Pipe (ফুয়েল পাইপ) | Faulty |  | Open | 07-Sep-26
SYL_X0092 | Moulavibazar | Moulavibazar | S-066 | DG | DG CB Problematic | Faulty |  | Open | 07-Sep-26
SYL_X0097 | 3 snag(s), 3 open
SYL_X0097 | Moulavibazar | Moulvibazar Sadar | S-067 | DG | DG room dusty | Faulty |  | Open | 07-Sep-26
SYL_X0097 | Moulavibazar | Moulvibazar Sadar | S-068 | DG | DG Room Light (ডিজি রুমের লাইট) | Faulty |  | Open | 07-Sep-26
SYL_X0097 | Moulavibazar | Moulvibazar Sadar | S-069 | DG | DG room roof tin faulty | Faulty |  | Open | 07-Sep-26
SYL_X0103 | 2 snag(s), 2 open
SYL_X0103 | Moulavibazar | Kulaura | S-003 | DG | Fuel pipe hard | Faulty |  | Open | 02-Sep-26
SYL_X0103 | Moulavibazar | Kulaura | S-004 | DG | Need to fuel tank lock system,& pipe protection | Faulty |  | Open | 02-Sep-26
SYL_X0105 | 3 snag(s), 3 open
SYL_X0105 | Moulavibazar | Kamalganj | S-040 | DG | (unspecified) | Faulty | DG canopy open due to hi temp issue, need to DG health check | Open | 03-Sep-26
SYL_X0105 | Moulavibazar | Kamalganj | S-041 | DG | (unspecified) | Faulty | ABC Faulty | Open | 03-Sep-26
SYL_X0105 | Moulavibazar | Kamalganj | S-042 | General | (unspecified) | Faulty | DG Room roof tin faulty | Open | 03-Sep-26
SYL_X0141 | 1 snag(s), 1 open
SYL_X0141 | Moulavibazar | Barlekha | S-005 | DG | DG overholing issue | Faulty |  | Open | 02-Sep-26
SYL_X0152 | 2 snag(s), 2 open
SYL_X0152 | Sunamganj | Tahirpur | S-053 | DG | DG power breaker faulty | Faulty |  | Open | 04-Sep-26
SYL_X0152 | Sunamganj | Tahirpur | S-054 | DG | Engine mountain broken | Faulty |  | Open | 04-Sep-26
SYL_X0156 | 3 snag(s), 3 open
SYL_X0156 | Sunamganj | Chhatak | S-020 | DG | Dg controller display not clean, Nothing on the display is visible | Faulty |  | Open | 03-Sep-26
SYL_X0156 | Sunamganj | Chhatak | S-021 | DG | Radiator ful block dust | Faulty |  | Open | 03-Sep-26
SYL_X0156 | Sunamganj | Chhatak | S-022 | DG | DG fan belt loose. | Faulty |  | Open | 03-Sep-26
SYL_X0191 | 3 snag(s), 3 open
SYL_X0191 | Sunamganj | Sunamganj Sadar | S-060 | DG | Lube oil level is low | Faulty |  | Open | 05-Sep-26
SYL_X0191 | Sunamganj | Sunamganj Sadar | S-061 | DG | MC 1 pole faulty | Faulty |  | Open | 05-Sep-26
SYL_X0191 | Sunamganj | Sunamganj Sadar | S-062 | DG | Need Overhaling | Faulty |  | Open | 05-Sep-26
SYL_X0213 | 2 snag(s), 2 open
SYL_X0213 | Moulavibazar | Barlekha | S-006 | DG | ATS hole filling nok | Not Available |  | Open | 02-Sep-26
SYL_X0213 | Moulavibazar | Barlekha | S-007 | DG | DG Room Light (ডিজি রুমের লাইট) | Faulty |  | Open | 02-Sep-26
SYL_X0221 | 1 snag(s), 1 open
SYL_X0221 | Sunamganj | South Sunamgonj | S-063 | DG | water pump leakage | Faulty |  | Open | 05-Sep-26
SYL_X0242 | 1 snag(s), 1 open
SYL_X0242 | Sunamganj | Sunamganj Sadar | S-012 | DG | Lube Oil Shortage | Faulty |  | Open | 03-Sep-26
SYL_X0247 | 2 snag(s), 2 open
SYL_X0247 | Sunamganj | Dowarabazar | S-015 | DG | DG canopy broken | Faulty |  | Open | 03-Sep-26
SYL_X0247 | Sunamganj | Dowarabazar | S-016 | DG | DG controller install proper way | Faulty |  | Open | 03-Sep-26
SYL_X0257 | 2 snag(s), 2 open
SYL_X0257 | Moulavibazar | Moulvibazar Sadar | S-013 | DG | Hi temp sensor | Faulty |  | Open | 03-Sep-26
SYL_X0257 | Moulavibazar | Moulvibazar Sadar | S-014 | DG | DG Rusty | Faulty |  | Open | 03-Sep-26
SYL_X0291 | 1 snag(s), 1 open
SYL_X0291 | Habiganj | Bahubal | S-070 | DG | DG Room roof tin faulty | Faulty |  | Open | 07-Sep-26
SYL_X0543 | 1 snag(s), 1 open
SYL_X0543 | Sunamganj | Dowarabazar | S-019 | DG | Dg Controller display not visible | Faulty |  | Open | 03-Sep-26
SYL_X0554 | 5 snag(s), 5 open
SYL_X0554 | Sunamganj | Derai | S-047 | DG | Lube oil level is low | Faulty |  | Open | 03-Sep-26
SYL_X0554 | Sunamganj | Derai | S-048 | DG | Need to overhaling issue because lube oil is leaking from the engine gasket. | Faulty |  | Open | 03-Sep-26
SYL_X0554 | Sunamganj | Derai | S-049 | DG | (unspecified) | Faulty | The fuel tank is installed in an open area, fuel could be stolen at any time. | Open | 03-Sep-26
SYL_X0554 | Sunamganj | Derai | S-050 | DG | Black smoke is coming out of the silencer pipe. | Faulty | With the engine turned off | Open | 03-Sep-26
SYL_X0554 | Sunamganj | Derai | S-051 | DG | when engine start | Faulty |  | Open | 03-Sep-26
SYL_X0615 | 2 snag(s), 2 open
SYL_X0615 | Moulavibazar | Kulaura | S-010 | DG | Fuel Pipe (ফুয়েল পাইপ) | Faulty |  | Open | 03-Sep-26
SYL_X0615 | Moulavibazar | Kulaura | S-011 | DG | Need to fuel pipe protection for fuel save | Faulty |  | Open | 03-Sep-26
TOTAL | 70 snag(s), 70 open